## 7-Day Plan
# | Day | Theme | Phase | Task | Deliverable | Owner | Status | Start Date | End Date | Notes
1 | 1 | Foundation & Infrastructure | Foundation | Unify the two repos into zatca-middleware-dev | Single Next.js + Supabase app, builds green | Claude | Done |  |  | Pushed
2 | 1 | Foundation & Infrastructure | Foundation | Supabase schema + migrations + RLS | 10 tables, tenant isolation | Claude | Done |  |  | migrations 001-003
3 | 1 | Foundation & Infrastructure | Foundation | Google authentication (Supabase Auth) + sessions | Login works end-to-end | Claude | Done |  |  | verified
4 | 1 | Foundation & Infrastructure | Foundation | Multi-tenant isolation + tenant bootstrap | Org + membership on first login | Claude | Done |  |  | DB-verified
5 | 1 | Foundation & Infrastructure | Foundation | Secret encryption (AES-256-GCM) | Credentials/keys encrypted at rest | Claude | Done
6 | 1 | Foundation & Infrastructure | Foundation | Env config + ZATCA env resolver (Demo/Real) | Configurable endpoints | Claude | Done
7 | 2 | ZATCA Core & Onboarding | ZATCA Core | Consolidate shared core (UBL XML, signing, QR) | Proven core in unified app | Claude | Done |  |  | from tested repos
8 | 2 | ZATCA Core & Onboarding | ZATCA Core | Wire onboarding (CSR -> compliance -> production) per tenant | Run onboarding per tenant | Claude | Done |  |  | simulation, OTP 123456
9 | 2 | ZATCA Core & Onboarding | ZATCA Core | Fix production CSID (real cert, not placeholder) | Valid production CSID | Claude | To Do |  |  | audit finding
10 | 2 | ZATCA Core & Onboarding | ZATCA Core | Validate core vs local ZATCA SDK (hash/sign) | Byte-match SDK reference | Claude | To Do |  |  | correctness gate
11 | 2 | ZATCA Core & Onboarding | ZATCA Core | Demo <-> Real environment switching | Per-tenant environment | Claude | In Progress
12 | 3 | Adapters & Async Pipeline | Adapters | Odoo adapter (JSON-RPC + webhook + write-back) | Odoo end-to-end | Claude | Done |  |  | ported in
13 | 3 | Adapters & Async Pipeline | Adapters | Zoho adapter (OAuth + webhook + write-back) | Zoho end-to-end | Claude | Done
14 | 3 | Adapters & Async Pipeline | Adapters | Real connection test + field provisioning | No fake 'connected' states | Claude | Done
15 | 3 | Adapters & Async Pipeline | Pipeline | Async jobs queue + /api/worker + retry/idempotency | Reliable async clearance | Claude | To Do |  |  | Doc 05 design
16 | 3 | Adapters & Async Pipeline | Pipeline | Verify invoice -> clearance -> write-back (simulation) | Cleared invoice persists | Claude | In Progress |  |  | needs migration 003
17 | 4 | Application Surfaces (UX) | UX | Navigable onboarding journey (clickable steps) | No dead-ends | Claude | Done
18 | 4 | Application Surfaces (UX) | UX | Business profile (seller identity) | Saves to organization | Claude | Done
19 | 4 | Application Surfaces (UX) | UX | Invoices list + detail (real tenant data) | Real invoices shown | Claude | Done
20 | 4 | Application Surfaces (UX) | UX | Dashboard: real KPIs + recent invoices | Live dashboard | Claude | To Do
21 | 4 | Application Surfaces (UX) | UX | Settings: connection / API keys / team | 3 settings screens | Claude | To Do
22 | 4 | Application Surfaces (UX) | UX | Remove old/dead pages (bank, register, admin) | One clean design + data model | Claude | To Do |  |  | cleanup
23 | 5 | Notifications, Go-Live & Admin | Notifications | Email alerts (Resend): failures + CSID expiry | Tenants notified | Claude | To Do
24 | 5 | Notifications, Go-Live & Admin | Go-Live | Demo -> Real (production onboarding) flow | Switch a tenant to live | Claude | To Do
25 | 5 | Notifications, Go-Live & Admin | Reliability | CSID expiry tracking + warnings | Warn at 30/14/3 days | Claude | To Do
26 | 5 | Notifications, Go-Live & Admin | Admin | CBT admin console (cross-tenant support) | Internal support view | Claude | To Do
27 | 5 | Notifications, Go-Live & Admin | Docs | API docs page (Mode B) + self-serve guides | Customer-facing docs | Claude | To Do
28 | 6 | Testing & QA | Testing | Unit tests (crypto / xml / qr / validation) | Green unit suite (~90%) | Claude | To Do
29 | 6 | Testing & QA | Testing | Integration tests (adapters / queue / write-back) | Green integration suite | Claude | To Do
30 | 6 | Testing & QA | Testing | E2E tests (Playwright: onboarding -> invoice) | Critical journeys covered | Claude | To Do
31 | 6 | Testing & QA | Testing | Compliance validation vs SDK (clear/report/notes) | Compliance proven | Claude | To Do
32 | 6 | Testing & QA | Security | Security pass (RLS isolation, secrets, rate-limit) | Hardened | Claude | To Do
33 | 6 | Testing & QA | Testing | Bug triage + fixes | Stable build | Claude | To Do
34 | 7 | Hardening, Deploy & Launch | Deploy | Vercel production deploy + env vars | Live public URL | Claude + User | To Do |  |  | user provides Vercel
35 | 7 | Hardening, Deploy & Launch | Deploy | Update Google/Supabase redirect URLs to live domain | Auth works in production | Claude + User | To Do
36 | 7 | Hardening, Deploy & Launch | Deploy | Smoke tests + monitoring/logging | Verified production | Claude | To Do
37 | 7 | Hardening, Deploy & Launch | Launch | Documentation + demo walkthrough | Handoff package | Claude | To Do
38 | 7 | Hardening, Deploy & Launch | Launch | UAT vs real ZATCA env + production cutover | Go-live readiness | User + ZATCA | To Do |  |  | external dependency
39 | 7 | Hardening, Deploy & Launch | Launch | Marketing: SEO/AEO on CBT website (parallel) | Discoverable product | User | To Do |  |  | GTM

## Status Summary
ZATCA Compliance Middleware — 7-Day Plan to Production
Convergent BT · Demo build on ZATCA simulation, then UAT, then Production
Overall
Total tasks
Done
In Progress
To Do
% Complete
Day | Theme | Tasks | Done | In Prog. | To Do
1 | Foundation & Infrastructure
2 | ZATCA Core & Onboarding
3 | Adapters & Async Pipeline
4 | Application Surfaces (UX)
5 | Notifications, Go-Live & Admin
6 | Testing & QA
7 | Hardening, Deploy & Launch
Legend
Done
In Progress
To Do